## Gantt
Exam Project | [5 empty] | Legend:
Abrace | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Project Lead |  | Project Start Date: |  | 2018-12-17
|  | Display Week: |  | 1 |  | 00 | [34 empty] | 00
 | time axis 2018-12-17 to 2019-02-10
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | mon | tu | wed | thur | fri | sat | sun | mon | tu | wed | thur | fri | sat | sun | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d | d
Milestone 1
Problem discription | Goal | Name |  | 2018-12-17 | 5 | Week 1 mon: 2; Week 1 tu: 2; Week 1 wed: 2; Week 1 thur: 2
Problem formultaion | Goal |  |  | 2018-12-17 | 5 | Week 1 mon: 2; Week 1 tu: 2; Week 1 wed: 2; Week 1 thur: 2
Research method | Goal |  |  | 2018-12-17 | 7 | Week 1 tu: 2; Week 1 wed: 2; Week 1 thur: 2; Week 1 fri: 2; Week 1 sat: 2; Week 1 sun: 2
Meeting with supervisor | Goal |  |  | 2018-12-21 | 1 | Week 1 fri: 2
Analysis and user research planned | Low Risk |  |  | 2018-12-21 | 3 | bar: Week 1 fri to Week 1 sun
Milestone 2
Analysis and user research executed |  |  | 60% | 2018-12-23 | 13
Meeting with supervisor | On Track |  | 50% | 2018-12-25 | 9
Task 3 | Low Risk |  | 33% | 2018-12-30 | 11
Task 4 | Milestone |  |  | 2019-01-01 | 1 | bar: Week 3 d
Task 5 |  |  |  | 2019-01-02 | 24
Milestone 3
Problem solution | On Track |  |  | 2019-01-01 | 4
Product development | Med Risk |  |  | 2019-01-04 | 14
Meeting with supervisor | On Track |  |  | 2019-01-19 | 6
Task 4 | Goal |  |  | 2019-01-23 | 3 | Week 6 d: 2; Week 6 d: 2; Week 6 d: 2
Task 5 | Low Risk |  |  | 2018-12-21 | 19
Milestone 4
Finish the report |  |  |  | 2019-01-26 | 15
Final adjustments of the product |  |  |  | 2019-02-01 | 5
Test of the product | Milestone |  |  | 2019-02-03 | 1 | bar: Week 7 d
Meeting with supervisor
Task 5
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.